## Stage 1
Category | Test | Status | Depends on | Comment
Command tests
| command_test_m.cmd | Done
| command_test_l.cmd | Done |  | Uses command_test_l.hex
| command_test_x.cmd | Done
| command_test_pc.cmd | Done
| command_test_dot.cmd | Done
| command_test_b.cmd | Done
Instructions for test harness
| harness_test_addi.cmd | Done |  | Initialization of expected result, assign 0 or 1 to pass, li
| harness_test_lui.cmd | Done |  | Initialization of expected result
| harness_test_bne.cmd | Done |  | Compare actual with expected result
| harness_test_jalr.cmd | Done |  | Jump to 0 for breakpoint
Instruction tests
| instruction_test_lui.s | Done
| instruction_test_addi.s | Done
| instruction_test_slti.s | Done
| instruction_test_sltiu.s | Done
| instruction_test_xori.s | Done
| instruction_test_ori.s | Done
| instruction_test_andi.s | Done
| instruction_test_slli.s | Done
| instruction_test_srli.s | Done
| instruction_test_srai.s | Done
| instruction_test_add.s | Done
| instruction_test_sub.s | Done
| instruction_test_slt.s | Done
| instruction_test_sltu.s | Done
| instruction_test_xor.s | Done
| instruction_test_or.s | Done
| instruction_test_and.s | Done
| instruction_test_sll.s | Done
| instruction_test_srl.s | Done
| instruction_test_sra.s | Done
| instruction_test_jal.s | Done | sub
| instruction_test_jalr.s | Done | jal, sub
| instruction_test_auipc.s | Done | jal, sub
| instruction_test_beq.s | Done | jal
| instruction_test_bne.s | Done | jal
| instruction_test_blt.s | Done | jal
| instruction_test_bge.s | Done | jal
| instruction_test_bltu.s | Done | jal
| instruction_test_bgeu.s | Done | jal
| instruction_test_lb.s | Done | auipc
| instruction_test_lh.s | Done | auipc
| instruction_test_lw.s | Done | auipc
| instruction_test_lbu.s | Done | auipc
| instruction_test_lhu.s | Done | auipc
| instruction_test_sb.s | Done | lw, auipc
| instruction_test_sh.s | Done | lw, auipc
| instruction_test_sw.s | Done | lw, auipc
| instruction_test_fence.s | Done |  | Test fence no-operation
| instruction_test_ecall.s | Done |  | Test ecall unimplemented
| instruction_test_ebreak.s | Done |  | Test ebreak unimplemented
| instruction_test_csr.s | Done |  | Test csrrw, csrrs, csrrc, csrrwi, csrrsi, csrrci illegal
Compiled programs
leaf
random
fib
sort
quicksort
thrash

## Stage 2
Category | Test | Description | Comment
Privilege
| prv_command | Set and show privilege level
CSR comand
| csr_cmd_read | Read all defined CSRs
| csr_cmd_read_invalid | Read undefined CSR gives error
| csr_cmd_set | Set writable CSR
| csr_cmd_set_unused_bits | Set unused bits of a writable CSR
| csr_cmd_set_read_only | Set read only CSR gives error
Breakpoint exceptions
| ebreak_mtvec | ebreak trap transfers to mtvec address, ignores mode field
| ebreak_mcause | ebreak trap sets mcause correctly
| ebreak_mepc | ebreak trap sets mepc correctly
| ebreak_mstatus_mpp | ebreak trap pushes privilege level stack correctly
| ebreak_mstatus_ie | ebreak trap pushes interrupt enable stack correctly
Return from exception
| mret_mepc | mret uses mepc for return address
| mret_mstatus_mpp | mret pops privilege level stack correctly
| mret_mstatus_ie | mret pops mstatus interrupt stack correctly
CSR instructions
| csr_instr_csrrw | Read/write a writable CSR | Incl rd is x0
| csr_instr_csrrs | Read/set a writable CSR | Incl rs1 register value is 0
| csr_instr_csrrc | Read/clear a writable CSR | Incl rs1 register value is 0
| csr_instr_csrrwi | Read/write immediate a writable CSR | Incl rd is x0
| csr_instr_csrrsi | Read/set immediate a writable CSR | Incl uimm value is 0
| csr_instr_csrrci | Read/clear immediate a writable CSR | Incl uimm value is 0
| csr_instr_csrrs_rs1_x0 | Read/set a read-only CSR using x0 as rs1 | When rs1 is x0, csr is not written. Check with read only csr.
| csr_instr_csrrc_rs1_x0 | Read/clear a read-only CSR using x0 as rs1 | When rs1 is x0, csr is not written. Check with read only csr.
| csr_instr_csrrsi_uimm_0 | Read/set immediate a read-only CSR using 0 as uimm | When uimm is 0, csr is not written. Check with read only csr.
| csr_instr_csrrci_uimm_0 | Read/clear immediate a read-only CSR using 0 as uimm | When uimm is 0, csr is not written. Check with read only csr.
Illegal instruction exceptions
| illegal_user_mret | Illegal instruction trap on mret in user mode
| illegal_csr_user_m | Illegal instruction trap on machine csr access in user mode
| illegal_csr_number | Illegal instruction trap on undefined csr number
| illegal_csr_read_only | Illegal instruction trap on write to read only CSR | Incl csrrs/c with rs1 not x0 and value = 0 trapping
Environment call exceptions
| ecall_user | ecall instruction executed in user mode
| ecall_machine | ecall instruction executed in machine mode
Misaligned exceptions
| misaligned_instr | Misaligned address during instruction fetch | pc is not a multiple of 4
| misaligned_load_lw | Misaligned address during lw load instruction | ld for which the effective address is not a multiple of 4
| misaligned_load_lh | Misaligned address during lh/lhu load instruction | lh/lhu or which the effective address is not a multiple of 2
| misaligned_store_sw | Misaligned address during sw store instruction | sw for which the effective address is not a multiple of 4
| misaligned_store_sh | Misaligned address during sh store instruction | sh or which the effective address is not a multiple of 2
Interrupts
| int_msip_read_only | mip.msip read only
| int_mtip_read_only | mip.mtip read only
| int_meip_read_only | mip.meip read only
| int_usip_read_write | mip.usip read/write
| int_utip_read_write | mip.utip read/write
| int_ueip_read_write | mip.ueip read/write
| int_usi_machine | User software interrupt (cause 0) in machine mode | Globally enabled iff mstatus.mie set
| int_msi_machine | Machine software interrupt (cause 3) in machine mode
| int_uti_machine | User timer interrupt (cause 4) in machine mode
| int_mti_machine | Machine timer interrupt (cause 7) in machine mode
| int_uei_machine | User external interrupt (cause 8) in machine mode
| int_mei_machine | Machine external interrupt (cause 11) in machine mode
| int_usi_user | User software interrupt (cause 0) in user mode | Globally enabled due to being in user mode, change to M mode
| int_msi_user | Machine software interrupt (cause 3) in user mode
| int_uti_user | User timer interrupt (cause 4) in user mode
| int_mti_user | Machine timer interrupt (cause 7) in user mode
| int_uei_user | User external interrupt (cause 8) in user mode
| int_mei_user | Machine external interrupt (cause 11) in user mode
| int_usi_vectored | User software interrupt (cause 0) in machine mode, vectored
| int_msi_vectored | Machine software interrupt (cause 3) in machine mode, vectored
| int_uti_vectored | User timer interrupt (cause 4) in machine mode, vectored
| int_mti_vectored | Machine timer interrupt (cause 7) in machine mode, vectored
| int_uei_vectored | User external interrupt (cause 8) in machine mode, vectored
| int_mei_vectored | Machine external interrupt (cause 11) in machine mode, vectored
| int_multiple_vectored | Multiple pending interrupts in machine mode, vectored
Assembled/compiled tests
| compiled_misaligned_load | C program does misaligned load uint32_t, exception handler emulates
| compiled_misaligned_instr | C program calls function at misaliged addr, exception handler replaces call
| compiled_illegal_instr | C program calls function with mul instr, exception handler replaces call
| compiled_ebreak | C program sets breakpoint on function entry, exception hander resumes
| compiled_ecall_machine | C program calls function to get/set IE, implemented by ecall exception handler
| compiled_ecall_user | C program calls function to get/set prv, implemented by ecall exception handler
| compiled_int_quicksort | C quicksort program run in user mode, multiple interrupts